Flood Extent Mapping & Prediction — Prayagraj (Ganga-Yamuna Confluence)

Project Status Report & 10-Day Roadmap to Predictive Baseline

# 1. Executive Summary

This project automates flood extent mapping for the Ganga-Yamuna confluence in Prayagraj using multi-sensor satellite data (Sentinel-1 SAR and Sentinel-2 optical) and a Python-based processing pipeline. The midsem phase (Phase 1) built and validated a complete detection pipeline: from raw satellite data ingestion through noise removal, thresholding, spatial cleanup, and an independent Random Forest classifier, producing a quantified flood extent of 128.25 sq km with 85.2% classification accuracy.

The original project brief calls for flood PREDICTION using historical data — forecasting flood extent before it happens, not just mapping it after the fact. Phase 1 (completed) is best understood as building the measurement tool and label-generation engine required for prediction, not prediction itself. This report documents current status, honestly scores where we stand, and lays out the next 2-3 days of work needed to establish a first genuine predictive baseline before we present.

# 2. Where We Currently Stand

On a 1-10 scale against the full 'flood prediction' goal, we assess ourselves at approximately 4/10 currently, with a realistic target of 6-7/10 achievable within 10 days (2-3 days for the highest-priority items below). The breakdown:

| Component | Points | Status | Notes |
| --- | --- | --- | --- |
| Data pipeline & preprocessing (SAR/optical ingestion, speckle filtering) | 1.5 | Done | GEE pull + median filter |
| Thresholding & spatial cleanup (Otsu tested → -16.0 dB deterministic cutoff, MMU) | 1.5 | Done | 128.25 sq km mapped |
| Detection ML baseline (Random Forest, SAR + pre-flood NDWI) | 1.0 | Done | 85.2% accuracy |
| Multi-event historical labeling (3-4 past floods) | 1.5 | In progress | Target: next 2-3 days |
| Precursor data acquisition (rainfall, river gauge levels) | 1.5 | In progress | Target: next 2-3 days |
| Predictive/forecasting model (precursor -> future extent) | 2.0 | Planned | First-pass baseline, days 7-8 |
| Temporal validation (held-out unseen flood event) + U-Net | 1.0 | Future scope | Endsem |

# 3. The Key Gap: Detection vs. Prediction

It's important the whole team understands this distinction clearly, since it will likely come up when presenting:

- What we've built (Phase 1): given SAR imagery DURING/AFTER a flood, classify which pixels are water and quantify the extent. This is descriptive/retrospective — it tells us where a flood was, after the fact.

- What true prediction requires: given data from BEFORE a flood (rainfall trends, river discharge, past flood history), forecast whether/where/how much flooding will occur at a future date — before it is visible in any satellite image.

- Our Random Forest currently classifies a pixel's state using SAR + NDWI values from that same point in time — it is not yet forecasting a future event.

This is a scoping issue, not a failure: our own project roadmap already frames Phase 1 outputs as pseudo-labels for a future U-Net model, which is the correct engineering sequence. The next 2-3 days are about starting Phase 2 (prediction) rather than deepening Phase 1 further.

# 4. What's Needed to Reach 6-7/10

Two things are missing before any predictive model can be built:

- Multi-event historical labeling — our pipeline currently covers only ONE flood event. We need 3-4 historical events mapped the same way to form a time series.

- Precursor/predictor data — rainfall (IMD/GPM/CHIRPS) and river discharge/gauge levels (CWC) for the days/weeks before each flood event. This is data we have not sourced at all yet.

Once both exist, even a simple regression or Random Forest trained on (rainfall, river level, season) → (flooded area) constitutes a legitimate first predictive baseline, and is enough to honestly claim 6-7/10 rather than 4/10.

# 5. 10-Day Roadmap

| Timeline | Task | Deliverable |
| --- | --- | --- |
| Days 1-2 | Pull SAR + optical for 2-3 additional historical Prayagraj flood events via existing GEE script; run through existing detection pipeline (median filter -> -16.0 dB threshold -> MMU cleanup) | Multi-event labeled flood-extent dataset |
| Days 3-4 | Source precursor data: cumulative rainfall (IMD/GPM/CHIRPS) and river discharge/gauge levels (CWC) for the 7-30 days before each flood event | Genuine 'past data' inputs for prediction |
| Days 5-6 | Assemble tabular dataset: [event_date, rainfall, river_level, season] -> target = flooded area / flood occurrence | Prediction-ready dataset |
| Days 7-8 | Train first predictive baseline (regression or Random Forest) on precursor variables | Working forecasting baseline |
| Day 9 | Hold out one full event, test whether prediction is directionally correct | Legitimate 'tested on unseen event' claim |
| Day 10 | Buffer + update slides/report with new results | Presentation-ready |

# 6. Risks & Honest Caveats

- Gauge/rainfall data availability for Prayagraj specifically may be the biggest bottleneck — not the modeling itself. We should start sourcing this on Day 1, in parallel with historical event mapping.

- With only 3-4 historical events, any predictive model will be statistically weak (small sample size). We should state this openly rather than overclaiming accuracy.

- Full temporal validation (testing on a genuinely unseen future event) and the planned U-Net segmentation model remain endsem-scale work — not achievable in this 10-day window, and we should not imply otherwise while presenting.

# 7. How We Plan to Present This

Rather than presenting this as '40% done,' the pitch will frame the project as two clearly scoped phases: Phase 1 (measurement & label-generation) — complete and validated, with strong quantitative results; Phase 2 (prediction) — in progress, with a first baseline forecasting model targeted before presentation. This is an honest and defensible framing that matches how the project was actually designed (pseudo-labels → predictive/U-Net model), and avoids overpromising on forecasting capability we haven't yet validated.

# 8. Immediate Next Actions (Next 2-3 Days)

- Confirm 3-4 historical Prayagraj flood event dates (last 10-15 years) — needs quick research/verification, not guessing.

- Re-run existing GEE + detection pipeline on each confirmed event to produce additional labeled flood masks.

- Begin sourcing rainfall (IMD/GPM) and river gauge (CWC) data in parallel — flag immediately if any source isn't programmatically accessible so we can find a substitute fast.

- Assemble the combined precursor + target dataset as soon as both pieces are available.

Prepared for team coordination — midsem status, 19 September 2026